Regional Scoring

Grade 4 ELA

3 – Day Option

(scoring 1 task per day)

Questions & Givens

How many papers will I score in region?

Grade 4 = 3,750

How many scorers will I need?

Given: Each paper has 3 tasks to score.  On scoring day, one teacher can score 60 listening or 50 writing or 50 reading tasks.

DAY 1

Listening

3,725/60 = 62 teachers

DAY 2

Writing

3,725/50 = 75 teachers

DAY 3

Reading

3,725/50 = 75 teachers

How many second scorers will I need?

Given: It is estimated that 10% of the papers will need a second reader.

DAY 1

Listening

372/60 = 7 teachers

DAY 2

Writing

372/50 = 8 teachers

DAY 3

Reading

372/50 = 8 teachers

How many table facilitators will I need?

Given: One table facilitator for 6 teachers scoring the same task.  One table facilitator for each task second scored.

DAY 1

Listening

69/6 = 11 teachers

DAY 2

Writing

83/6 = 14 teachers

DAY 3

Reading

83/6 = 14 teachers

RWADA Distribution for Test Scoring

February 2000

ELA - Grade 4

3 – Day Option

(scoring 1 task per day)

| District Share | Grade 4 Students |
| --- | --- |

| Scorers | Table Facilitators |
| --- | --- |
| Bloomfield | .02767 | 103 | 6 | 1 |
| Canandaigua | .09514 | 350 | 22 | 4 |
| Clyde-Savannah | .02552 | 89 | 6 | 1 |
| Dundee | .02256 | 73 | 5 | 1 |
| Gananda | .02366 | 93 | 6 | 1 |
| Geneva | .05540 | 236 | 13 | 2 |
| Honeoye | .02539 | 95 | 6 | 1 |
| Lyons | .02919 | 106 | 7 | 1 |
| Marion | .02773 | 92 | 7 | 1 |
| Naples | .02195 | 65 | 5 | 1 |
| Newark | .06296 | 191 | 15 | 2 |
| North Rose | .04320 | 164 | 10 | 2 |
| Palmyra-Macedon | .05139 | 200 | 12 | 2 |
| Penn Yan | .05017 | 169 | 12 | 2 |
| Phelps-Clifton Springs | .04915 | 149 | 12 | 2 |
| Red Creek | .02742 | 100 | 6 | 1 |
| Red Jacket | .02427 | 85 | 6 | 1 |
| Romulus | .01380 | 58 | 3 | 1 |
| Seneca Falls | .03801 | 123 | 9 | 2 |
| Sodus | .03734 | 147 | 9 | 1 |
| Victor | .06549 | 243 | 15 | 2 |
| Waterloo | .04563 | 159 | 11 | 2 |
| Wayne | .06325 | 243 | 14 | 2 |
| Whitman | .04128 | 121 | 10 | 2 |
| Williamson | .03271 | 115 | 8 | 1 |
| Private |
| 156 |
| TOTALS: |
| 3725 | 235 | 39 |

Regional Scoring

ELA - Grade

3 – Day Option

(scoring 1 task per day)

| Pro’s | Con’s |
| --- | --- |

More people get staff development opportunity.

Less impact on substitute pool.

Less impact on students.

Lessens sick day problem.

More flexibility.

Lessens burnout.

Larger pool of people to choose from if additional scoring time is necessary.

District has choice as to using the same people or different people each day (flexibility).

Have already done a successful 3-day model.

Cost is higher.

Creating specialists reduces flexibility.

Regional Scoring Budget

Grade 4  ELA

3 – Day Option

(using different teachers each day & scoring 1 task per day)

3,725 papers

3 training leaders

39 table facilitators

235 scorers (212 scorers + 23 second readers)

Scoring Assistants (2 days X 10 assistants & 3 days X 20 assistants @ $130/day)		$10,400

Clerical Support (.1 FTE – covered through core)							        ($  2,500)

Site Coordinator (.2 FTE)												$  8,000

Training Leaders (6 days X 3 leaders X $300/day)								$  5,400

Scoring Day (refreshments, site, meals, copying) 3 days X 115 X $35				$12,075

Supplies (covered through core)										        ($  1,000)

$35,875 / 3,725  =  $9.63 per test

plus sub costs and EduTech charges