# Lyons Central School District

Technology Plan

2004-2007

# Providing a Budget for Technology 	Page 16

Assessing Technology Plans Goals	Page 17

## Conclusion	Page 18

Appendix	Page 19

### Student Acceptable Use Policy for Technology

Laptop Release Agreement form for Staff

Digital Camera Release form for Staff

Foreword

The Board of Education of the Lyons Central School District has committed itself to ensuring that each student will be:

- A Self Directed Learner

- A Critical Thinker and Problem Solver

- Academically Proficient

- A Responsible Citizen

- An Effective Communicator

In order to ensure that each student graduates with the information and skills needed to exist in a technologically advanced society, the Board of Education recognizes the need to integrate technology throughout students’ educational experiences.  The Board of Education’s commitment to providing updated and accessible technology is essential not only for a strong technology program but for a comprehensive education that incorporates technology throughout.

In terms of technological growth, our school district can be proud of the progress made over the past ten years.  It is only with the continued support of the Board of Education that we will continue forward movement.

Acknowledgements

The Lyons Central School District’s Technology Planning Committee acknowledges the following for their support.

# The Board of Education

- Fred Bragan, Superintendent

- David Alena, Asst. Supt. For Business

- Mark Cazer, Project Manager, EduTech

- Anyone else who provided input regarding the technology needs for the district.

Lyons Central School Technology Planning Committee

## David Alena	Assistant Supt. For Business

Kathie Polyn	Computer Coordinator

Anne Cook	First Grade Teacher

Pam Crandall	Computer Lab Assistant

Steve Leo	Network Administrator

Paul Meade 	M.S. Technology Teacher

Robert Morsdorf	H.S. Technology Teacher

Brenda Neal	Elementary Computer Teacher

Gary Verdine	Second Grade Teacher

Stephan Wlodarczyk	Sixth Grade Teacher

Denise Cline	M.S. and H.S. Librarian

Methodology & Current Status

In the winter of 2004 the Technology Committee met to review our past Technology plan.  Many of the goals from our previous plan had been attained while others were ongoing and have become part of this plan.  Furthermore, with changing technologies some new goals were added.

Since the last Plan was adopted three years ago Lyons School District has made significant gains in technology.

The District now has three Smart Boards, one for each building. Smart Board training and integration of lesson plans occurred over the 2003 summer.

The District participates in shared educational television channel to inform the community of upcoming and past school events.

The District continues to expand its' school web page for parents, the community, students and staff.  New additions to the site are:

- PASS, (a Parental Access Support System) that provides feedback to parents/guardians on their student's grades; student schedule and school calendar;

- Daily homework by grade & subject;

- Links for staff to Data mentor and NY State Virtual Learning;

- Athletic schedule and films clips highlighting school games;

- School lunch menus;

- Additional Teacher web pages;

- Technology Guidelines and procedures for staff such as Network log on procedures, network-printing procedures, email procedures, virus scan procedures, Administrative curriculum guides, and frequently asked technology questions.

- Future expansion of the web will include Highlights of the student handbook, administrative forms and library research links.

The District is moving forward to introduce students to new multimedia communications through the use of film equipment and software.  The computer club offers students the opportunity to learn how to build computer workstations.  The Art department offers students independent study courses to further develop computer graphic skills.  The elementary lab through various grants continues to offer an extensive robotics program.

A renovation project is underway which will include a new computer lab for Middle School and High School students and students in the Art program.  Furthermore a multimedia/research lab is planned for Elementary School Library.

The Junior/Senior High School has the following technology:

- MST lab (12 computers)

- Cad lab	(17 computers)

- Art Lab (9 computers)

- PC lab (28 computers)

- Business Lab (26 computers)

- Library Lab (14 computers)

- All District file servers (4 )

- Multimedia  Lab- formerly RAITIN room (1 computer, document camera, projector, 2 VCRs, fax)

- All English classes have mini labs (5 workstations)

- 2 Science labs have 5 mini labs (s workstations)

- Laptops for staff (10)

- 9 digital cameras

- 1 cam corder

- 1 dv cam corder

- 8 projectors

- Each classroom has 6 network drops

- At least 1 computer workstation

- HS Resource room has a mini lab (6 computers)

- MS Resource room has 1 computer and 1 laptop

- 7 scanners

The Elementary School

- Computer lab (28 computers)

- Second computer lab  (15 workstations)

- 6 network drops per classroom

- All grade level classrooms have more than one computer & a g3 processor

- All special teachers have a power Mac

- 4 Digital Cameras

- 1 dv camcorder

- 4 projectors

- 6 Laptops

- 2 scanners

Out of School Suspension Facilities –

10 Computers on a separate network

Bus facilities

Workstations with remote access to student records database system

# District Wide

- All buildings are networked

- Computer Coordinator

- Network Administrator

.

Introduction

The Technology Planning Committee, with the support of staff, Administration and the Board of Education, is dedicated to providing the District with a technological vision for the future.  By establishing a multi- year plan, the committee will give direction for the District in the following areas:

#### Objective #1: Providing a technological educational environment, which will enable the student to become a productive, responsible member of society.

- Increasing  student access to technology

- Increasing integration of technology & curriculum

- Providing user Support

## Objective #2: Having a Professional Development Plan for learning new and existing Technologies

- Providing teachers with the opportunity for technology training

- Providing support to teachers for implementing new technologies

- Integrating the technology Professional Development Plan with overall District Professional Development Plan

- Increasing use of  electronic communication access by staff

- Providing electronic student record systems and training to staff

- Maintaining a Professional Development tracking system of staff courses and hours.

### Objective #3: Requiring an Assessment of Technology for improving education by

- Assess facilities and hardware equipment for technology growth

- Evaluate new educational technologies available for instruction

- Increase use of multimedia equipment for presentations

# Maximize utilization of printing equipment and minimize its financial cost

# Evaluating & purchasing educational software to meet student needs

- Evaluating District technology policies & determining if additional policies need to be established and or revised.

Objective #4: Providing for a budget to obtain and maintain hardware, software, professional development and other services

- Developing a plan of fund allocation

##### Developing a plan for outside sources

#### Objective #5: Providing for an assessment of Goals in Technology Plan

##### Developing assessment tools to measure students’ ability to use and integrate technology

- Reporting on each goal in the Technology Plan (on ‘Update & Evidence’ chart) at year-end to determine if goal has been obtained.

- Review Plan on a yearly basis & update as necessary

- At end of three years, review previous plan & prepare a new three year plan for the District

Objrctive 1. Providing a Technological Environment

### REQUIREMENT/GOAL: Increasing student access to technology

| # Timeline | Solutions | Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| 2004-2007 | Plan for technology growth | Renovation Project More labs Wireless cart for classroom use | Architect, BOCES | Students using lab Staff & students using wireless cart | Tech Comm. Admin Staff |
| ## 2004-2007 | Computer labs opened beyond school hours (before & after) | Grants to fund plan Students teaching classes for community | Adult Aide Students | Students using labs after school Students earning community service points Community using school computers | Tech Comm. |
| ## 2004-2007 | Wireless Laptops/ handheld for students | Mobile cart used in classroom instruction Remote Access points in place for Internet use Policies & Procedures in place | Staff training | Students using Wireless laptops | Tech. Comm |
| ## Ongoing | Provide access to students with special needs | Continue to assess special needs of students with staff Attend workshops on special needs software/ hardware Continue Evaluating market solutions | Training for staff and students using new software/hardware. | Students using new technology | Computer Coordinator CSE Administration Staff |
| ## Ongoing | Provide other technological alternatives for learning | On line courses through BOCES Providing older computers to students who are in need | Update Administrators guidance, Dept. Heads, regarding programs | Students taking on line courses | Computer Coordinator Network Administrator Administration |

###### Objective 2.Having a Professional Development Plan

###### EQUIREMENT/Goal: Increase integrate of Technology & curriculum

| # Timeline | Solutions | Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| # Ongoing | #### Ensure integration of software into curriculum | Computer Coordinator/ Elementary computer teacher will work with staff to integrate technology objectives with curriculum Staff will continue to merge technology and curriculum in lessons where feasible. Staff will set a technology goal yearly with Administration | Staff Development Curriculum Writing | Teacher lesson plans/ classroom projects. Shared lesson plans on web for other district staff to access Continue to identify how software is meeting curriculum objectives | Computer Coordinator Teachers Admin. Elementary Computer teacher |

#### REQUIREMENT/GOAL: Provide User support

| # Timeline | Solutions | ##### Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing | Evaluate technical support needs | Analyze service request, project priorities Establish Timeline for major projects and resources projects Update network and work workstations with current operating systems and applications Have current protection procedures for computer viruses in place. | Technical Support BOCES | Service request, future and ongoing projects Timeline detailing major projects Network and work stations having current operating systems and applications | Computer Coordinator Network Administrator |

REQUIREMENT/GOAL: Providing Teachers with the opportunity for technology training and curriculum integration.

| # Timeline | ### Solutions | Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing | Technology Training opportunities | In house training Out of house training During school day Summer After school Determine what staff needs to know to use technology Develop and implement a staff training plan Update plan as necessary for new technologies | In-house experts TRC EduTech Universities | Increase in workshop participation | Computer Coordinator |

###### REQUIREMENT/GOAL: Providing support to teachers for implementing new technologies

| # Timeline | Solutions | Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing | Assistance from Staff, Computer Coordinator, Network Administrator, Students Financial compensation Release time New equipment software | Research feasibility Purchase equipment Purchase software Installation /configuration of equipment Provide Training | Technology Committee Training during school year & summer | New technology implemented | Computer Coordinator Network Administrator Technology Committee |

###### REQUIREMENT/GOAL; Technology Professional Development Plan should integrate with overall District Professional Development Plan

| # Timeline | ##### Solutions | Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| # Ongoing | Incorporate technology goal into overall teacher goals | ## Goal setting with Principals/ Administration Teachers incorporate a technology goal in PDP | Goal will include necessary training | Teacher implementing technology | Computer Coordinator Network Administrator Teacher Principal |

###### REQUIREMNT/GOAL: Increase usage of student records maintained and accessed electronically.

| # Timeline | Solutions | ##### Strategies/Steps | Training Needed/ Support | Update/ ### Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing | Staff will use School Master program for Recording all student information (attendance, grades, scheduling, appointments, health information, bus routes) Staff will use Web based Clear Trac 200 for students EIPs Staff will use Data Mentor to (web based analysis of student performance on ELA test) Administrators will use Cognos Data warehouse for analysis of test reporting | Have appropriate hardware available to staff workstations and PDAs Have staff trained on PDAs as needed MS/HS staff maintains period by period attendance Implement new modules to student database such as AIS Have staff trained on Clear Trac 200 Customize data fields on databases to accommodate LCSDs requirements. - Document all Staff responsibilities in maintenance of databases - Train MS/HS on Gradebook module. - Cross train support staff on student database tasks. | Train new teachers on grading (ms/h.s.) Train office staff new modules | Staff using software and hardware to input and retrieve student data and create reports Parents accessing student data through PASS link. | Computer Coordinator Network Administrator Admin BOCES Guidance staff |

Requirement/Goal:  Maintaining a Professional Development tracking system of staff courses and hours.

| # Timeline | Solutions | Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| 2004-7 | Web based PDP system | Convert existing database to a more thorough & accessible tracking system |  |  |  |

###### REQUIREMENT/GOAL: Increase Electronic District communications access

| # Timeline | Solutions | Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing | Maintenance of email accounts for all district staff | Provide email training for new staff Provide user support Communicate updates to email system | Staff training on e-mail Troubleshoot discrepancies | Directory of accounts | Computer Coordinator |
| 2004-7 | Increase Staff using electronic communications to parents | Training on docushare, front page Setting up docushare accounts Increasing options on web based PASS system Staff Web pages Training on Gradebook Implementation of web based Clear Trac 200 for EIPs Staff sending communications for school tv channel Web based sports program | Staff training | Increase access to web for District information | Computer Coordinator |

Objective 3.  Requiring an Assessment of Technology

REQUIREMENT/GOAL: Assess facilities and hardware equipment for technology growth

| # Timeline | ##### Solutions | ### Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing | Provide for technology resources for new relocated and renovated classrooms | Meet with architects, staff, BOCES, Administrators to determine plans Evaluate other schools district facilities | Architect needs to understand expectations & incorporate in his design | New classrooms with plenty of space for technology | Admin. Computer Coordinator Tech Comm |
| Ongoing | Examine continuing server space Examine network | Meet with BOCES to determine needs | BOCEs network staff | Servers and network working efficiently | Computer Coordinator Technician |

Requirement/GOAL: Evaluate new educational technologies available for instruction

| # Time- line | Solutions | Strategies/steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing | Keep abreast of new technology | Committee members continue to provide input Tech. Coordinator will send appropriate information to staff In-service Representative(s) sent to technology meetings, conferences & shows Joint Technology Coordinator meetings Keep staff informed of new technologies/ software/ hardware/web based applications | Attend technology meetings/ conferences Journals Email Listservs | On-going reports Presentations Staff using new technologies | Tech. Committee Tech. Coordinator Administrators |
| 2006-7 | Update the computer curriculum objectives as needed | Review objectives | Requests by Staff | Staff integrating objectives | Tech. Committee Computer Coordinator |
| Ongoing | Maintain software inventory | Create a database to maintain data | Computer Coordinator | Software inventory |  |
| Ongoing | Maintain Hardware inventory | Evaluate inventory databases | Technician | Data collected | Computer Coordinator Technician |

## REQUIREMENT/GOAL: Increase use of multimedia equipment for presentations

| # Timeline | ###### Solutions | Strategies/steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing | Develop staff awareness of what is available | Multimedia presentations at faculty &/or dept./ grade level meetings Superintendent’s Conference Day focusing on technology | Tech. Committee | Faculty meeting Newsletter Email New teacher orientation Administrators/ staff/ students using multimedia | Computer Coordinator Tech. Committee |
| Ongoing | Individual teachers/ students will request multimedia equipment (video cameras, movie editing software) | Set up multimedia equipment & procedures Provide user support | Training on multimedia equipment | Multimedia Log sheet Staff/Students using video equipment and video editing software | Tech. Comm. |
| Ongoing | Complete Technology Assessment Inventory | Evaluate inventory |  | Inventory Documented | Tech Coordinator Technician |
| Ongoing | Reevaluate multimedia needs | Review requests on log sheets |  | Requests Teacher demand | Computer Coordinator Tech Com Admin |

# REQUIREMENT/Goal:  Maximize utilization of printing equipment and minimize financial cost

| # Time- line | Solutions | ##### Strategies/steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| 2004-07 | Evaluate district printing needs and make recommendation | Establish printing guidelines for staff/students Evaluate other districts plans Prepare inventory/cost of current equipment & supplies Determine if new technologies are more feasible. Recommend alternative solutions to decrease printing cost | Vendor presentations Review printing systems | Reports from vendors | Tech Committee Admin Computer Coordinator |

# REQUIREMENT/GOAL: Evaluating & purchasing educational software to meet student needs

| # Time line | ##### Solutions | Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing | Coordination & recommendation of software purchases based upon purchasing procedure | Continue line item software budget Individual teachers complete software request form for instructional software (May also be completed as a grade level or department) Consider network vs stand alone licensing Review inventory to prevent duplication |  | Software request forms Updated list of district software | Computer Coordinator |
| # Ongoing | #### Determine if software is being integrated into curriculum | Computer Coordinator will work with staff to integrate software |  | Teacher lesson plans/ classroom projects. Elementary rubrics & assessment by Computer Teacher EIP Teacher for 11th graders (Skill checks) | Computer Coordinator Teachers Administrators |

Requirement/Goal:  Evaluating District technology policies & determining if additional policies need to be established and or revised.

| # Timeline | Solutions | Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing | Policies updated & published | Review other School District policies on similar issues Update policies as needed Inform Staff & students on changes | Published and staff students notified | Staff/Students Handbooks Published on Web | Technology Committee Administrators |

Objective #4: Providing for a budget to obtain and maintain hardware, software, professional development and other services

- Developing a plan of fund allocation

##### Developing a plan for outside sources

Objective 5.  Assessing Terchnology Plan Goals

REQUIREMENT/GOAL: Develop appropriate assessment tools to measure student ability to use technology

| # Timeline | Solutions | ### Strategies/Steps | Training Needed/ Support | Update/ Evidence | Person(s) Responsible |
| --- | --- | --- | --- | --- | --- |
| Ongoing | Knowledge & integration of District’s K-12 Technology curriculum | Review Technology Curriculum Review Technology Curriculum at dept./curriculum meetings &/or faculty meetings Publish on web Integrate technology into portfolio development ## See staff training Elementary assessment & reporting MS – MST assessment HS – 11th grade assessment & reporting | Technology Committee supports building curriculum efforts focusing on technology integration | Utilization of Technology curriculum | Tech. Comm. |
| Ongoing | Update & maintain assessment tools | Rubrics Review Technology Objectives | Rubric training Software training | Students will demonstrate the use of technology in their benchmark presentations and at agrade levels | Tech. Comm. |
| Ongoing | Evaluate student technology skills and application | Students will be evaluated before & after grade levels to determine if curriculum objectives have been met. | Clear expectations of curriculum outcomes at each grade level | Students will improve technical skills | Building Principals |

REQUIREMENT/GOAL: Report on each goal in Technology Plan at year-end to determine if goal has been met.

REQUIREMNT/GOAL: Review Plan on a yearly basis & update as necessary

REQUIREMENT/GOAL: At end of three years review plans and prepares a new plan for District

Conclusion

The mission statement of Lyons Central School is to  “enable each student to become a productive member of society”.  In today’s competitive and ever-changing world, such commitment is not possible without careful attention to the role of technology.  Therefore the Technology Committee has strived to develop a plan that will allow technology to be integrated into all curriculums.  This will help insure the success of our district in preparing our students for the 21st century.

We also believe technology should support the district’s goal of life-long learning.  Therefore community access to our technology is an important part of the plan.

While mindful of the financial constraints of the district, the technology committee feels strongly that the cost of implementing this plan is a worthwhile and necessary investment in the future of our students and community-at-large.  The committee requests the district’s support in implementing this plan.

Appendix

Lyons Central School District

Student Acceptable Use Policy

for Computer Technology

Overview

With Computer Technology comes an electronic network that provides vast, diverse and unique resources. Our goal is to provide teachers, staff, and students with up-to-date computer technology including access to the Internet. We believe however, that the use of this technology within the Lyons School District is a privilege, not a right, and that certain guidelines must be adhered to.

Guidelines

A. 	Educational Purpose

1. 	Internet access has been established for educational purposes only, which include classroom activities, career development, and educational projects consistent with Lyons School district policy.

2. 	Students are expected to follow the rules set forth in the Lyons Jr.-Sr. High School Student Handbook/or Elementary building policies that may apply to the use of computer technology.

3. 	Students may not use the Internet for commercial purposes. Students may not offer, provide, or purchase products or services through the Internet.

B. 	Student Access.

1. 	All students will have access to the Internet World Wide Web information resources wherever available. Students in grades K-12 using the Internet will be under adult supervision.

2. 	All students will have access to computer technology.

- Access to the Internet and to district computer technology is not a right but a privilege and unacceptable usage will result in revoking this privilege.

4. 	If and when individual e-mail accounts become available for students, the students will need additional authorization from their parents or guardians.

5. 	Students training in safety and “ etiquette “ in the use of the Internet will be required before student use is allowed.

C. 	Unacceptable Uses

1. 	E-mail and the Internet

a. 	Students will not post personal contact information about themselves or other people. Personal contact includes information regarding home addresses, telephone, school address, work address, etc.

b. 	Students will not agree to meet with somebody they have met on-line.

c. 	Students will promptly disclose to their teacher or other school employee any message they receive that is inappropriate or makes them feel uncomfortable.

2. 	Software

a. 	Students will not download software from the Internet.

b. 	Students will not make illegal copies of District software. 	When software is purchased it is licensed for a particular computer or group of computers. To use software in a manner that is not in compliance with the software license is an infringement of copyright laws.

c. 	Students will not load software from floppies, CD-ROM, or external hard drives.

3.	 Illegal Activities

a. 	Students will not attempt to gain unauthorized access to any other computer systems through the Internet access, or go beyond authorized access. This includes attempting to log in through another person’s account or access another person’s files. These actions are illegal, even if only for the purposes of “ browsing “.

b. 	Students will not make deliberate attempts to disrupt the computer system or destroy data by spreading computer viruses or by any other means. These actions are illegal.

c. 	Students will not use the Internet to engage in any other illegal act, such as arranging for the sale or purchase of illegal drugs which includes alcohol and cigarettes, engaging in criminal gang activity, or threatening the safety of person[s], etc.

4. 	System Security

a.	Students are responsible for their individual accounts and should take all reasonable precautions to prevent others from being able to use their password to another person.

b. 	Students will immediately notify an administrator or the technology coordinator if they have identified a possible security problem.

c. 	If a security problem is detected by a student, that student will not identify this problem to anyone other than those specified above.

d. 	Students will avoid the inadvertent spread of computer viruses by following the Lyons School District virus protection procedures.

e. 	Any other user identified as a security risk may be denied access.

5. 	Inappropriate Language

- Students will not use obscene, profane, lewd, vulgar, rude, inflammatory,

threatening, or disrespectful language.

- Students will not post information that could cause damage or danger of

disruption to the computer network.

c. 	Students will not engage in personal attacks, including those that are prejudicial or discriminatory.

d. 	Students will not harass another person. Harassment is persistently acting in a manner that distresses or annoys another person. If a student is told by a person to stop sending them messages, the student will do so.

e. 	Students will not knowingly or recklessly post or defamatory information about a person or organization.

6. 	Respecting Resource Limits

a. 	Students will use the system only for educational and career development activities.

- Students will not download files to the computer unless approved by a

supervising adult.

c. 	Time allocation is set for each student by attending supervisor.

d. 	An Internet Access Form must accompany each on-line use activity.

7. 	Plagiarism and Copyright Infringement

a. 	Students will not plagiarize works on the Internet. Plagiarism is taking the ideas or writings of others and presenting them as if they were theirs.

b. 	Students will respect the rights of copyright owners. Copyright infringement occurs when someone inappropriately reproduces a work that is protected by a copyright. If a work contains language that specifies appropriate use of that work, students should follow the expressed requirements. If students are unsure whether or not work can be used, consult with a teacher or librarian.

8. 	Access to Inappropriate Material

a. 	Students will not use the Internet or any other computer technology to access material that is pornographic or obscene. Students will not access material that advocated illegal acts, violence or discrimination towards other people.

b.	 If a student mistakenly, accesses inappropriate information, that student should immediately tell a teacher, administrator or technology coordinator. This will be documented and will protect the student against a claim that student has intentionally violated this policy. However, if a student repeatedly accesses inappropriate information, a review will be done to determine if access was truly accidental.

c. 	If there is material that a parent feels inappropriate for their child to use, the Lyons School District fully expects that the student will follow their parent’s instructions in this matter.

D. 	Students rights

1. 	Free speech

Technology communication is considered a limited forum, similar to the school newspaper, and the Lyons school District may restrict student’s speech for valid

educational reasons.

2. 	Search and Seizure

a. 	Students should expect only limited privacy in the contents of their personal files on the Lyons School District system. Teachers, administrators and the technology coordinator will have access to all student files on the Lyons School District’s instructional network. This excludes administrators files pertaining to the student’s personal information.

b.	Routine maintenance and monitoring of the Lyons School District’s networks may lead to discovery that a student has violated this policy, as stated in the Student Handbook, or the law.

c. 	An individual search will be conducted if there is reasonable suspicion that a student has violated; Student Acceptable Use Policy for Use of computer Technology, Student Handbook, or the law.

d. 	Parents have the right at any time to request to see the contents of their child’s account.

e. 	Network storage areas may be treated like school lockers. Network administrators may review files and communications to maintain system integrity and insure that 	users are using the systems responsibly. Users should not expect that files stored on district servers will always be private.

3. 	Due Process

a. 	The Lyons School District will cooperate fully with local, state, or federal officials in any investigation related to any illegal activities conducted through the Internet or the Lyons School District Network[s].

b. 	In the event there is a claim that a student has violated this policy in the use of   computer technology, the student will be provided with the written notice of the suspected violation and an opportunity to be heard in the manner set forth in the Lyons Central School Student Handbook.

c.	Lyons School District administrators will make the final determination as to what constitutes unacceptable use and their decision is final.

d. 	If the violation also involves a violation of other provisions of the Lyons Central School Student Handbook, it will be handled in a manner described in the Lyons Central School Handbook. Additional restrictions may be placed on student’s

use of their Internet account.

4.	Limitation of Liability

The Lyons School District makes no guarantee that the functions or the services provided by or through the Lyons School District system will be error-free or without defect. The Lyons School District will not be responsible for any damage incurred, including but not limited to, loss of data or interruptions of service. The Lyons School District is not responsible for the accuracy or quality of the information obtained through or stored on the system. The Lyons School District

will not be responsible for any financial obligations arising through the

unauthorized use of the system.

5.	Personal Responsibility

It is the student’s responsibility to use computer technology, both inside and outside of school, in a proper, lawful fashion. Failure to use computer technology appropriately may result in any or all of the following depending on the infraction.

Verbal warning

Loss of Internet use

Limited use of computer technology

Loss of access to computer technology

Loan of District Technology Equipment

Loans are to ber recorded and that equipment be returned upon request of somenone from the media center.  All equipment is to be used for classroom instruction purposes.  Digital cameras cannot be used by staff members for an extended period of time.

It is also understood that equipment be returned in the same working condition which it was borrowed, allowing for reasonable wear and tear due to normal use.  The borrower assumes responsibility for any loss or damage beyond reasonable use.

Staff responsible for equipment:

Name:			Grade and Room no.

Building:			Phone

Date taking equipment 		Date expected to return

Please stat in writing purpose or goal, project.

I will be financially responsible for equipment replacement if broken, stolen or lost.

Signature of staff taking equipment			Today’s Date

Approved:

Building Principal: 				Date:

Equipment Type:  Laptop		Digital camera            Digital camcorder

Model no.				Serial no.

Other items: