ELBA CENTRAL SCHOOL

DISTRICT PROFESSIONAL DEVELOPMENT PLAN

Goal:  By June 2003, the District will develop clearly defined expectations for student performance in writing at all grade levels.

Objectives:

- Teachers will develop a common understanding and language of the essential traits of writing.

- Teachers will engage in professional development in the 6-Trait Writing Assessment and Instruction model.

- Teachers will develop a K-12 Curriculum Guide for writing.

| Strategies | Activities | Who | Timeframe (2002-2003) | Performance Measure/ Data Source |
| --- | --- | --- | --- | --- |
| 6-Trait Exploration | - Book talk facilitated by SLT/SETRC coordinator - Attending conferences - Collegial circles - Guest speakers - Classroom visitation - PDP projects, including but not limited to: - Research on the web - Viewing/discussing videotapes of 6-Trait implementation - Handbook of common language | All K-12 faculty K-12 faculty members K-12 faculty members | Sept.-Jan Sept.- June Sept.-June | Participant Evaluation PDP approval APPR |
| Rubric development and implementation | - PDP projects, including but not limited to - Develop grade level rubrics - Collect student writing as samples for grade level rubrics - Share K-12 rubrics, sample papers and instructional strategies for writing. | K-12 faculty members | Sept.-June | Rubrics and sample papers |
| Development of Writing Curriculum Guide | - PDP projects | K-12 faculty members | Sept.-June | Curriculum Guides |