Regional Scoring

Grade 8 ELA

3-Day Option

(scoring 1 task per day)

Questions & Givens

| How many papers will I score in region? |  | Grade 8 = 3,800 |
| --- | --- | --- |
| How many scorers will I need? Given: Each paper has 3 tasks to score. On scoring day, one teacher can score 60 tasks for listening, and 50 tasks for reading and writing. |  | Listening 3,800/60 = 64 teachers Writing 3,800/50 = 76 teachers Reading 3,800/50 = 76 teachers |
| How many second scorers will I need? Given: It is estimated that 10% of the papers will need a second reader. |  | Listening 380/60 = 7 teachers Writing 380/50 = 8 teachers Reading 380/50 = 8 teachers |
| How many table facilitators will I need? Given: One table facilitator for 6 teachers scoring the same task. One table facilitator for each task second scored. |  | Listening 71/6 = 12 teachers Writing 84/6 = 14 teachers Reading 84/6 = 14 teachers |

RWADA Distribution for Test Scoring

June 2000

ELA - Grade 8

3-Day Option

(scoring 1 task per day)

|  | District Share | Grade 8 Students | Scorers | Table Facilitators |
| --- | --- | --- | --- | --- |
| Bloomfield | .02767 | 99 | 7 | 1 |
| Canandaigua | .09514 | 380 | 23 | 4 |
| Clyde-Savannah | .02552 | 101 | 6 | 1 |
| Dundee | .02256 | 88 | 5 | 1 |
| Gananda | .02366 | 84 | 6 | 1 |
| Geneva | .05540 | 207 | 13 | 1 |
| Honeoye | .02539 | 81 | 6 | 1 |
| Lyons | .02919 | 99 | 7 | 1 |
| Marion | .02773 | 106 | 7 | 1 |
| Naples | .02195 | 87 | 5 | 1 |
| Newark | .06296 | 246 | 15 | 3 |
| North Rose | .04320 | 165 | 10 | 2 |
| Palmyra-Macedon | .05139 | 198 | 12 | 2 |
| Penn Yan | .05017 | 156 | 12 | 2 |
| Phelps-Clifton Springs | .04915 | 190 | 12 | 2 |
| Red Creek | .02742 | 106 | 6 | 1 |
| Red Jacket | .02427 | 92 | 6 | 1 |
| Romulus | .01380 | 45 | 3 | 1 |
| Seneca Falls | .03801 | 126 | 9 | 1 |
| Sodus | .03734 | 128 | 9 | 1 |
| Victor | .06549 | 248 | 16 | 3 |
| Waterloo | .04563 | 159 | 11 | 2 |
| Wayne | .06325 | 222 | 15 | 3 |
| Whitman | .04128 | 168 | 10 | 2 |
| Williamson | .03271 | 128 | 8 | 1 |
| Private |  | 132 |  |  |
| TOTALS: |  | 3800 | 239 | 40 |

Regional Scoring

ELA - Grade 8

3-Day Option

(scoring 1 task per day)

| Pro’s | Con’s |
| --- | --- |
| - Less impact on substitute pool. - Less impact on students. - Lessens sick day problem. - More flexibility. - We have already done a three-day model with success. - District has choice as to using the same people or different people each day (flexibility). | - Creating specialist reduces flexibility. |

Regional Scoring Budget

Grade 8 ELA

# 3 – Day Option

# (scoring 1 task per day)

3,800 papers

3 training leaders

40 table facilitators

239 scorers (216 scorers + 23 second readers)

Scoring Assistants (2 days X 10 assistants & 3 days X 20 assistants @ $130/day)		$10,400

Clerical Support (.1 FTE – covered through core)							        ($  2,500)

Site Coordinator	 (.2 FTE)												$  8,000

Training Leaders (6 days X 3 leaders X $300/day)								$  5,400

Scoring Day (refreshments, site, meals, copying) 3 days X 117 X $35				$12,285

## Supplies (covered through core)										        ($  1,000)

$36,085 / 3,800  =  $9.50 per test

plus sub costs and EduTech charges