ELBA CENTRAL SCHOOL

DISTRICT PROFESSIONAL DEVELOPMENT PLAN

Goal: By June 2005, the district will have a complete set of Curriculum Guides for all areas, courses, grade levels and subjects.

Objectives:

- Teachers know the Curriculum Guide model.

- Teachers develop Curriculum Guides.

- Develop a common electronic location for Curriculum Guides.

- Evaluate Curriculum Guides.

| Strategies | Activities | Who | Timeframe (2002-2003) | Performance Measure/ Data Source |
| --- | --- | --- | --- | --- |
| Teach each other | Presentation: - Introduction - Small group exploration (K-4; 5-8; 9-12) - Share examples/models - Vocabulary handout | Superintendent SLT facilitators | August 28 August 29 | Reaction of small groups Group leader assessments |
| Use of DocuShare | - Work with EduTech to develop a site - Faculty training - Work on DocuShare | Superintendent EduTech/ Tech Coord. Teachers | By September 1 By November 1 | Site exists Each K-12 faculty member has password and logged in |
| Curriculum Guide development | - Propose PDP to supervisor - Implement PDP | K-12 faculty members | By October 15 By June of school year | PDP Approval APPR |
| Evaluation | - Review curriculum guides | Supervisors/ Curriculum Specialist | Ongoing | Curriculum Guides are aligned with model and approved for publication |